Catholic Charities of Louisville

Strategic Plan—FINAL

Rev. 11-01-2020

| Focus Area 1: Awareness |  |  |  |  |
| --- | --- | --- | --- | --- |
| Goal 1.1 CCL has a developed a comprehensive branding strategy which inspires volunteers and donors and positions itself within the social services community. |  |  |  |  |
| Objectives |  | Timing | Accountability | For consideration as operational plans are developed |
| 1.1.1 | Review and refine the presentation of CCL’s brand: what it stands for, what value it promises to deliver to the community, what image it projects, etc. | Q1 2021 | Director of Development | - Charitable outreach of the local Catholic church - Convener and catalyst for charitable collaboration - Seek an umbrella that covers the breadth of CCL Programs |
| 1.1.2 | Review and refine the elements of CCL’s brand: logo, taglines, voice, and tone. | Q1 2021 | Director of Development | - Include “WHY” we serve (leveraging the best of our Catholic social values) - Include “WHO” we serve (all people in need, regardless of race, creed, or culture) |
| Goal: 1.2 CCL has raised brand awareness and become “top of mind” within the Catholic community and on the short list of respected organizations among entities performing charitable works and social services within the broader community. |  |  |  |  |
| Objectives |  | Timing | Accountability | For consideration as operational plans are developed |
| 1.2.1 | Develop and monitor a dashboard of metrics that measure the effectiveness of CCL’s communications in establishing awareness of CCL and its work. | Begin Q1 2021 and ongoing | Director of Development | - Research best practices regarding awareness tracking - Conduct an annual survey to gauge awareness and CCL fluency among various stakeholder groups |
| 1.2.2 | Become a storytelling organization. - Maintain collections of stories/data that illustrate the challenges faced by clients and showcase the impact of CCL’s work. - Develop a set of talking points and a scripted “elevator pitch” that describes CCL’s work, its motivation, and its impact. | Ongoing | Director of Development coordinates, CCL Leadership Team engages | - Ensure all functions understand the critical nature of this effort and become storytellers for their programs - Provide semi-annual updates to ensure “fresh” material |
| 1.2.3 | Relentlessly communicate CCL’s brand internally (board, staff, parishes, volunteers) and externally (those it serves, stakeholders, partners, funders). | Q1 2022 and ongoing | Director of Development coordinates, CCL Leadership Team engages | - Develop a CCL passport summarizing vision, mission, and values, distribute to all employees - Ensure employee and volunteer onboarding/orientation emphasizes who we are, what we do, and why we do it |
| 1.2.4 | Develop and implement a comprehensive communication plan that provides effective reach across all user groups and consistent messaging across all media platforms. | Q1 2022 | Director of Development | - Define key user groups to enable enhanced message targeting - Provide overlays to reach underserved groups, notably youth/young adults and individuals not involved with the institutional Church |
| 1.2.5 | Further establish CCL’s reputation among media outlets and other stakeholders as a resource for data, information, expertise, and impact stories regarding the communities it serves. | Q1 2022 | Director of Development |  |

| Focus Area 2: Engagement |  |  |  |  |
| --- | --- | --- | --- | --- |
| Goal 2.1 CCL has more fully integrated its work into the life of the parish, encouraging greater parish engagement in social ministry. |  |  |  |  |
| Objectives |  | Timing | Accountability | For consideration as operational plans are developed |
| 2.1.1 | Develop and implement a strategy to provide on-going support and user-friendly resources to assist parishes in social ministry. | Begin Q1 2021 and ongoing | Director of Mission | - Develop and implement a parish metrics tool for annual fluency evaluations - Consider annual 110 parish “blitz” similar to Covid-19 calls |
| 2.1.2 | Ensure CCL stakeholders (board, volunteers, pastors, parishioners, influencers) are fluent in Catholic Social Teaching and its connection to CCL’s work. - To include developing CST seasonal prayer services. - To include CST resource packets aligned with Days of Dignity | Q3 2021 annual assess-ment and ongoing | Director of Mission | - Provide state of the art tools to promote CST and how to put it into action - Promote social ministry in response to Catholic Social Teaching as an integral part of Catholic life motivating individuals to live in service to compassion and justice. Make real the charge at the end of Mass to go out and serve, live the Gospel. |
| 2.1.3 | Explore making CCL programming more accessible by taking it “on the road” to parishes and communities within the Archdiocese, increasing parishes’ awareness of CCL’s work and the options for engagement. | Q3 2021 and ongoing | Directors of Mission, Programs |  |

| Goal 2.2 CCL is recognized within the Archdiocese and the social services community as a collaborator, convener, and catalyst. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Objectives |  | Timing | Accountability | For consideration as operational plans are developed |
| 2.2.1 | Continue collaborating with key Archdiocesan leaders seeking synergies across programming areas. | Ongoing | CEO and CCL Leadership Team |  |
| 2.2.2 | Convene annual community forums, conversations, and learning experiences to address issues and practices related to social services and social justice. | Q2 2021 and ongoing | Director of Mission |  |
| 2.2.3 | Working in partnership with other Catholic and like-minded organizations, facilitate individual civic participation by collecting, cataloguing, and communicating opportunities to engage in the community. | Begin Q1 2022 and ongoing | Directors of Administration, Development |  |
| Goal: 2.3: CCL has broadened its base of support by engaging individuals/organizations that desire to be part of the Catholic Charities Community. |  |  |  |  |
| Objectives |  | Timing | Accountability | For consideration as operational plans are developed |
| 2.3.1 | Build a robust database to track the Catholic Charites Community (individuals who have engaged CCL’s mission in any way). | Q2 2021 and ongoing | Director of Development |  |
| 2.3.2 | Develop and implement a “multi-touch” relationship building plan to tell the CCL story and inspire friends to engage. | Q2 2021 and ongoing | Director of Development | - Set annual goals for growth of the Catholic Charities Community (C3) - Explore non-traditional means of “friend-raising” |
| 2.3.3 | Strategically enhance digital communications to expand reach, especially to underserved groups such as young people/young adults and individuals not involved in the institutional church. | Q1 2022 and ongoing | Director of Development |  |
| 2.3.4 | Develop and implement a strategy to engage young people/young adults who are socially conscious and looking for opportunities to contribute to the community. - Include outreach to local Universities and Catholic High Schools - Include partnerships to assist with outreach to young people/young adults | Q3 2022 and ongoing | Directors of Programs, Development |  |

| Focus Area 3: Programming |  |  |  |  |
| --- | --- | --- | --- | --- |
| Goal 3.1 CCL has demonstrated operational excellence and community impact with existing programming. |  |  |  |  |
| Objectives |  | Timing | Accountability | For consideration as operational plans are developed |
| 3.1.1. | Continue annual program evaluation process assessing operational effectiveness, program outcomes, community impact and financial sustainability. | Q1 2021 repeated annually | Board Program Committee, Director of Programs |  |
| 3.1.2 | Conduct an annual assessment of highest and best use of available funds with respect to program sunset/continuance/expansion and new program opportunities. | Q2 2021 repeated annually | CEO, Director of Finance, Board Finance Committee |  |
| Goal 3.2 CCL has ensured that its programming reflects the intersection of agency’s core competencies and critical community needs. |  |  |  |  |
| Objectives |  | Timing | Accountability | For consideration as operational plans are developed |
| 3.2.1 | Develop and implement a process to identify CCL’s core competencies and the community’s most prominent needs, and evaluate current programming against those criteria. | Q2 2021 | Director of Administration, Programs |  |
| 3.2.2 | Explore opportunities to leverage core competencies against the community’s most prominent unmet needs. | Begin Q1 2022 and ongoing | Director of Programs |  |
| Goal 3.3 CCL has utilized process and discipline when considering program expansion and/or new program implementation. |  |  |  |  |
| Objectives |  | Timing | Accountability | For consideration as operational plans are developed |
| 3.3.1 | When considering program expansion, establish priority focus in 4 critical areas: - Expanding services in the West End of Louisville and immediate CCL neighborhood - Expanding services in rural areas of the Archdiocese - Leveraging core competencies to a broader immigrant population - Programs that offer enhanced parish engagement | Q1 2021 | CEO | - Listen to key stakeholders in the established priority areas - Explore “best practice” programs from other network contacts - Evaluate partnerships and collaborations with allies and like-minded groups - Conduct feasibility studies on best options |
| 3.3.2 | Develop and implement a rubric to evaluate new programming opportunities that assesses fit to mission, core competencies, staff capacity and financial sustainability. | Q3 2021 | Director of Administration |  |
| Focus Area 4: Social Justice |  |  |  |  |
| Goal 4.1 CCL’s commitment to social justice is clear and unquestioned within the broader community and deeply understood and embraced within the organization itself. |  |  |  |  |
| Objectives |  | Timing | Accountability | For consideration as operational plans are developed |
| 4.1.1 | Intentionally and consistently connect CCL’s programming to Catholic Social Teaching and issues of social justice when communicating about its work. | Begin Q1 2021 and ongoing | Directors of Mission, Development |  |
| 4.1.2 | Discern and then clearly articulate CCL’s “voice” as it relates to social justice. | Q3 2021 | Director of Mission, CEO | - Build on CCL’s foundational programs and established reputation as a trusted partner on social issues - Collaborate with appropriate ADOL contacts |
| 4.1.3 | Become a steady champion for social justice, continuously drawing the community’s attention to chronic social issues and challenges. | Begin Q1 2022 and ongoing | Director of Mission |  |

| Focus Area 5: Revenue Generation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Goal 5.1 CCL has successfully completed the Building a Better Future capital campaign. |  |  |  |  |
| Objectives |  | Timing | Accountability | For consideration as operational plans are developed |
|  | See Building a Better Future capital campaign strategy and workplans for details. | Q2 2022 | Board Campaign Chair, CEO |  |
| Goal 5.2 CCL has implemented critical policies and procedures to support its revenue generation efforts. |  |  |  |  |
| Objectives |  | Timing | Accountability | For consideration as operational plans are developed |
| 5.2.1 | Develop a metric of funding sources; set annual goals for grants and fundraising and establish funding expectations for each department/program. | Q2 2021 and ongoing | Directors of Development, Finance; CEO |  |
| 5.2.2 | Engage 100% of the CCL Board in CCL’s development effort via: - Friend-raising to support Awareness Goal 2.3 - Give/Get financial support - Attendance at key CCL events (i.e. Rouler) - Commitment to thank key donors | Q2 2021 and ongoing | Board Chair, Director of Development |  |
| 5.2.3 | Determine the necessary board-designated financial reserve and fully fund it as funds are available. | Q2 2021 and ongoing | Board Chair, Board Finance Committee, Director of Finance |  |
| 5.2.4 | Establish a staff culture around revenue generation and development characterized by financial literacy, active support of development efforts, and ownership of development outcomes. | Q3 2021 and ongoing | CCL Leadership Team |  |
| 5.2.5 | Develop and implement a multi-tiered strategy for individual donor recognition. | Q4 2021 and ongoing | Director of Development | - Annual giving society - Recognition levels with special events (i.e. Dinner with Lisa or ABK) - Gifting guidelines for key donors |
| 5.2.6 | Expand use of donor analytics to drive development decision-making. | Q4 2021 and ongoing | Director of Development |  |
| Goal 5.3 CCL has broadened its base of funders and increased support, thus providing steady and sustainable funding for existing programs and potential program expansion. |  |  |  |  |
| Objectives |  | Timing | Accountability | For consideration as operational plans are developed |
| 5.3.1 | Refine processes and procedures to increase governmental and private grant funding | Ongoing | Director of Development | - Determine amount of grant activity needed to secure necessary funding - Prioritize options - Establish connections - Continue relationship building, especially with large local foundations |
| 5.3.2 | Expand funding opportunities through partnerships with corporations and community organizations. | Ongoing | Director of Development |  |
| 5.3.3 | Develop and implement a fundraising calendar targeting an increase in free-will donations. | Q1 2022 and ongoing | Director of Development | - Grow annual Rouler fundraising event - Explore solicitation of significant multi-year asks (i.e. 5 years @$1000) - Explore opportunities to leverage community fundraising events (i.e. Give for Good) - Explore opportunity to add an additional major fundraiser to the calendar |
| 5.3.4 | Fully leverage the funding potential of CCL’s social enterprises. | Q3 2022 | Director of Development | - Effectively market existing social enterprises to enhance revenue potential - Leverage CC-USA network to research best practices for social enterprise expansion, evaluating seemingly viable options using the process outlined in Objective 3.3.2 |
| 5.3.5 | Develop and implement a legacy/planned giving program. | Q2 2023 and ongoing | Director of Development | - Collaborate with the ADOL Advancement team - Leverage the wisdom of estate planning experts - Expand awareness of the CCL Endowment as a giving opportunity - Educate legal trust companies, raising awareness of CCL’s work and its connections to their clients’ interest |

| Focus Area 6: Staff and Volunteers |  |  |  |  |
| --- | --- | --- | --- | --- |
| Goal 6.1 CCL employees are confident in their work, flourishing personally as well as professionally. |  |  |  |  |
| Objectives |  | Timing | Accountability | For consideration as operational plans are developed |
| 6.1.1 | Enhance programs that recognize and celebrate good work. | Q1 2021 and ongoing | Human Resources Director, Staff Care Committee |  |
| 6.1.2 | Develop a culture of continuing professional development that assesses staff development needs and organizes appropriate staff training. | Q2 2021 and ongoing | Human Resources Director, Director of Administration | - Provide opportunities for both inter- and intra-departmental cross-training. |
| 6.1.3 | Increase staff and volunteer fluency in all of CCL’s work, enabling them to be confident ambassadors for the organization. | Begin Q1 2022 and ongoing | Human Resources Director, CCL Leadership Team | - CCL Passport can be a powerful tool when seeking to “seed” a new branding strategy - Leader-led training cascades demonstrate top-down agency endorsement |
| Goal 6.2 CCL’s Catholic identity is consciously fostered and embraced across the agency. |  |  |  |  |
| Objectives |  | Timing | Accountability | For consideration as operational plans are developed |
| 6.2.1 | Develop and offer opportunities to share faith collectively including Advent/ Lenten prayer services and Mass when appropriate. | Q1 2021 and ongoing | Director of Mission |  |
| 6.2.2 | Continue intentional efforts to educate staff as to Catholic Social Teaching in connection with the policies, work, and social justice initiatives of the agency. | Q1 2021 and ongoing | Director of Mission, Staff Care Committee |  |
| 6.2.3 | Continue to develop and enhance each program’s identification with patron saints and underlying principles of Catholic Social Teaching. | Q3 2021 and ongoing | Director of Mission |  |
| Goal 6.3 CCL embraces and leverages the rich diversity of the staff team, commits to breaking down work silos, and operates as one Catholic Charities. |  |  |  |  |
| Objectives |  | Timing | Accountability | For consideration as operational plans are developed |
| 6.3.1 | Continue intentional efforts to increase awareness of and effectively work across the cultural differences among staff. | Q1 2021 and ongoing | Staff Care Committee |  |
| 6.3.2 | Develop and enhance opportunities for staff members to learn about the work of CCL outside of their own departments. | Q1 2022 and ongoing | Director of Development, Staff Care Committee |  |
| 6.3.3 | Develop and execute a plan to leverage the synergy of bringing together the staff team in the new Catholic Charities Center. | Q4 2022 and ongoing | Director of Administration, HR Director, Staff Care Committee |  |

| Goal 6.4 CCL team has achieved the capacity to effectively manage the workload. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Objectives |  | Timing | Accountability | For consideration as operational plans are developed |
| 6.4.1 | Ensure staff has capacity to meet unforeseen challenges and opportunities as well as capacity for creative and strategic thinking. | Q3 2021 and ongoing | Directors of Programs, Administration; Program Directors | - Research and implement technological solutions to reduce paperwork, enhance work and information flow, and increase efficiency. |
| 6.4.2 | Develop new protocol around planning for department/program growth, including plans for recruiting, hiring, and evaluating new staff members. | Q4 2021 and ongoing | Director of Administration, Human Resources Director |  |
| 6.4.3 | Continue to explore and strategically employ shared staffing arrangements, interns, and volunteers to build staff capacity. | Q3 2022 and ongoing | Directors of Administration, Programs; Human Resources Director |  |